## Summary
Invensoft ERP-XBS-Automation Tracker
S.no. | Modules | Total | Completed | In Progress | Pending | % Completed
1 | PURCHASE - Basic flow for direct GRN withShipping Instruction.Purchase Contract - Create -> Purchase Contract - Review -> Shipping Instruction - Create -> Shipping Instruction - Review -> Goods Receipt Note - Create | 6 | 2 | 1 | 3 | 33.33%
2 | PURCHASE - LOCAL FLAT PRICE - Basic flow for direct GRN without Shipping Instruction Purchase Contract - Create -> Purchase Contract - Review -> Goods Receipt Note - Create | 6 | 0 | 0 | 6 | 0%
3 | TICKETING PURCHASE - User has recorded the ticket details and allocated the Flat price purchase contract to the ticket. Purchase Contract - Create -> Purchase Contract - Approval -> Ticket Create -> Ticket Review -> Ticket 1st Weight -> Warehouse Intake/Dispatch -> Ticket 2nd Weight -> Ticket Purchase Allocation. | 6 | 0 | 0 | 6 | 0%
4 | SALES - Basic flow for direct DC withShipping Instruction Sales Contract - Create -> Sales Contract - Review -> Shipping Instruction - Create -> Shipping Instruction - Review -> Goods Dispatch Note - Create | 6 | 0 | 0 | 6 | 0%
5 | SALES - LOCAL FLAT PRICE - Basic flow for direct DC without Shipping Instruction Sales Contract - Create -> Sales Contract - Review -> Goods Dispatch Note - Create | 6 | 0 | 0 | 6 | 0%
6 | TICKETING SALES - User has recorded the ticket details and allocated the Flat price sales contract to the ticket. Sales Contract - Create -> Sales Contract - Approval -> Ticket Create -> Ticket Review -> Ticket 1st Weight -> Warehouse Intake/Dispatch -> Ticket 2nd Weight -> Ticket Sales Allocation. | 6 | 0 | 0 | 6 | 0%
| Total | 40 | 2 | 1 | 6 | 5%
S.no. | Overall | Count | Execution Result | Count | Open work by Priority | In Progress | Pending | Total Open
1 | Total scenarios | 110 | Pass | 4 | High | 0 | 14 | 14
2 | Completed | 78 | Fail | 0 | Medium | 1 | 13 | 14
3 | In Progress | 1 | Skipped | 0 | Low | 0 | 1 | 1
4 | Pending | 28 | Not Run | 1
5 | Blocked | 2
6 | % Completed | 70.91%
7 | Proposed in 'To Add' sheet | 28

## Purchase-flow
Purchase Order Flow
PUR-GRN-SI-001
Step | Module | Action/Test Data | Expected Result | Autoamation Scripts
1 | Purchase Contract - Create | COFFEE-PURCHASE LOCAL FLAT PRICE @200 INR/Kg, Vendor 1, Robusta Cherry RC RAW 20 MT | Contract created successfully | Completed
2 | Verification | Dashboard & Commodity Contract Report | Details displayed correctly | Completed
3 | Contract Review | Approve contract | Contract approved | Completed
4 | Verification | Dashboard & Report | Details updated correctly
5 | Shipping Instruction Create | RC RAW 10 MT | SI created successfully
6 | SI Review | Approve SI | SI approved
7 | GRN Create | RC RAW 10 MT | GRN created successfully
8 | Verification | Dashboard, Commodity Contract Report, GRN Summary | Data reflected correctly
PUR-GRN-NO-SI-001
Step | Module | Action/Test Data | Expected Result | Autoamation Scripts
1 | Purchase Contract - Create | COFFEE-PURCHASE LOCAL FLAT PRICE @200 INR/Kg, Vendor 1, RC RAW 10 MT | Contract created | Completed
2 | Contract Review | Approve contract | Contract approved | Completed
3 | GRN Create | RC RAW 10 MT | GRN created
4 | Verification | Dashboard, Commodity Contract Report, GRN Summary | Data verified
PUR-TICKET-001
Step | Module | Action/Test Data | Expected Result | Autoamation Scripts
1 | Purchase Contract Create | RC RAW 10 MT | Contract created | Completed
2 | Contract Review | Approve contract | Contract approved | Completed
3 | Ticketing Create | Inbound GRN Ticket | Ticket created
4 | Ticket Review | Approve Ticket | Ticket approved
5 | 1st Weight | 15 MT | Weight recorded
6 | Purchase Intake | 400 Units, 25 KG PP Bags, Net 10000 KG, Gross 10100 KG | Intake recorded
7 | 2nd Weight | 4.9 MT Empty Truck | Allocation and GRN auto created
8 | Transaction Mapping | Ticket Qty 10 MT, GRN Qty 10 MT | Allocation completed
9 | Verification | Dashboard, Commodity Contract Report, GRN Summary | Data verified

## Sales-flow
Sales Flow
SALES-GDN-SI-001
Step | Module | Action/Test Data | Expected Result | Autoamation Scripts
1 | Sales Contract Create | COFFEE-Sales LOCAL FLAT PRICE @200 INR/Kg, Customer 1, RC A 20 MT | Contract created
2 | Verification | Dashboard & Commodity Contract Report | Details verified
3 | Contract Review | Approve contract | Contract approved
4 | Shipping Instruction Create | RC A 10 MT | SI created
5 | SI Review | Approve SI | SI approved
6 | Goods Dispatch Note Create | RC A 10 MT | GDN created
7 | Verification | Dashboard, Commodity Contract Report, GDN Summary | Data verified
SALES-GDN-NO-SI-001
Step | Module | Action/Test Data | Expected Result | Autoamation Scripts
1 | Sales Contract Create | COFFEE-Sales LOCAL FLAT PRICE @200 INR/Kg, Customer 1, RC A 10 MT | Contract created
2 | Contract Review | Approve contract | Contract approved
3 | Goods Dispatch Note Create | RC A 10 MT | GDN created
4 | Verification | Dashboard, Commodity Contract Report, GDN Summary | Data verified
TICKET-SALES-001
Step | Module | Action/Test Data | Expected Result | Autoamation Scripts
1 | Sales Contract Create | RC A 10 MT | Contract created
2 | Contract Review | Approve contract | Contract approved
3 | Ticketing Create | Goods Dispatch Note (Outbound) | Ticket created
4 | Ticketing Review | Approve ticket for Customer 1 | Ticket approved
5 | 1st Weight Outbound | 15 MT | Weight recorded
6 | Ticket Sales Dispatch | 400 Units, 25 KG PP Bags, Net 10000 KG, Gross 10100 KG | Dispatch details recorded
7 | 2nd Weight | 4.9 MT Empty Truck | Auto allocation and GDN created
8 | Reports Verification | Commodity Contract Report & GDN Summary | Reports verified
9 | Ticket Transaction Mapping | Ticket Qty 10 MT, GDN Qty 10 MT | Contract allocation completed

## Dependencies
# | Type | Dependency | Maven coordinates (groupId:artifactId) | Version | Version defined in | Used for | Review | Note / Action
1 | Language | Java | - | 21 | maven.compiler.release | Language level (compiler release) | OK
2 | Library | Selenium Java | org.seleniumhq.selenium:selenium-java | 4.47.0 | selenium.version property | Browser automation (Edge, Chrome, Firefox) | OK
3 | Library | TestNG | org.testng:testng | 7.11.0 | testng.version property | Test runner and assertions | OK
4 | Library | Cucumber Java | io.cucumber:cucumber-java | 7.34.7 | cucumber.version property | Gherkin step definitions | OK
5 | Library | Cucumber TestNG | io.cucumber:cucumber-testng | 7.34.7 | cucumber.version property | Runs Cucumber features through TestNG | OK | Keep on the same version as cucumber-java
6 | BOM | Allure BOM | io.qameta.allure:allure-bom | 2.29.0 | allure.version property | Manages Allure library versions | OK | Imported in dependencyManagement
7 | Library | Allure Cucumber 7 JVM | io.qameta.allure:allure-cucumber7-jvm | 2.29.0 (from BOM) | Allure BOM | Allure reporting for Cucumber 7 | OK
8 | Library | AspectJ Weaver | org.aspectj:aspectjweaver | 1.9.22 | aspectj.version property | Needed by Allure for @Step weaving | Check | No argLine -javaagent in surefire. Only needed if you use Allure @Step; otherwise the plain Cucumber plugin does not need it.
9 | Library | Log4j2 API | org.apache.logging.log4j:log4j-api | 2.25.2 | log4j.version property | Logging API (log.info) | OK
10 | Library | Log4j2 Core | org.apache.logging.log4j:log4j-core | 2.25.2 | log4j.version property | Logging implementation | OK
11 | Library | Log4j2 SLF4J2 binding | org.apache.logging.log4j:log4j-slf4j2-impl | 2.25.2 | log4j.version property | Routes Selenium SLF4J logs to Log4j2 | OK | Fixes the no SLF4J providers warning
12 | Library | Commons Configuration2 | org.apache.commons:commons-configuration2 | 2.11.0 | Hardcoded in dependency | Update values.properties | OK | Move version to a property for consistency
13 | Library | Commons Lang3 | org.apache.commons:commons-lang3 | 3.17.0 | Hardcoded in dependency | Utility classes (needed by Configuration2) | Check | Older release; newer versions address published security advisories. Check Maven Central.
14 | Library | Commons BeanUtils | commons-beanutils:commons-beanutils | 1.9.4 | Hardcoded in dependency | Needed by Configuration2 builders | Check | Older release; newer versions address published security advisories. Check Maven Central.
15 | Library | Jackson Databind | com.fasterxml.jackson.core:jackson-databind | 2.17.2 | Hardcoded in dependency | JSON test data and capturedValues.json | Check | Check for a newer 2.x patch release on Maven Central.
16 | Plugin | Cucumber for Java, Gherkin, TestNG, Allure, SonarLint, .ignore.Maven Compiler Plugin | org.apache.maven.plugins:maven-compiler-plugin | 3.14.1 | maven.compiler.plugin.version | Compiles with release 21 | OK
17 | Plugin | Maven Surefire Plugin | org.apache.maven.plugins:maven-surefire-plugin | Not set (Maven default) | No version in plugin block | Runs tests (mvn test, pipeline) | Action | maven.surefire.plugin.version = 3.5.4 is defined but never used. Add <version>${maven.surefire.plugin.version}</version> to the plugin.
18 | Config | Surefire testFailureIgnore | maven-surefire-plugin configuration | true | Plugin configuration | Keeps the build green when tests fail | Action | Failing tests will not fail the Azure DevOps pipeline (CCM-013/109). Remove or set false for pipeline runs.
19 | Plugin | Allure Maven Plugin | io.qameta.allure:allure-maven | 2.12.0 | allure.maven.version | Generate Allure report | Action | installDirectory C:/tools/allure-cli is a Windows path and will fail on Linux pipeline agents. Make it a property or remove it for pipeline runs.
20 | Tool | Allure Report CLI | reportVersion in allure-maven | 2.20.1 | allure-maven configuration | Version of the report generator | Check | Differs from the Allure library version 2.29.0; consider aligning. Also confirm allure.properties sets allure.results.directory=target/allure-results, as the plugin reads that folder.
Counts
OK | 12
Check | 5
Action | 3

## Scenarios
ID | Area | Module | Scenario / Checklist Item | Status | Priority | Category | Execution Result | Defect / Reference | Notes
CCM-001 | Selenium framework setup | Project Setup | Java 21,Intellij IDE andMaven project configured | Completed | High | Framework
CCM-002 | Selenium framework setup | Dependencies | Selenium TestNG Cucumber and Allure dependencies configured | Completed | High | Framework
CCM-003 | Selenium framework setup | POM | LoginPage and CommodityContractManagementPage implemented | Completed | High | Framework
CCM-004 | Configuration | DriverFactory | Browser driver initialization and configuration | Completed | High | Framework
CCM-005 | Configuration | Configuration | URL browser username and password configuration | Completed | High | Framework
CCM-006 | Reusalble utilities | Utilities | Reusable explicit wait utility implemented | Completed | High | Framework
CCM-007 | Reusalble utilities | Utilities | Scroll into view utility implemented | Completed | Medium | Framework
CCM-008 | Reusalble utilities | Utilities | JavaScript click utility implemented | Completed | Medium | Framework
CCM-009 | Reusalble utilities | Utilities | Element highlight utility implemented | Completed | Medium | Framework
CCM-010 | Reusalble utilities | Allure | Failure screenshot and Allure reporting implemented | Completed | Medium | Reporting
CCM-011 | Hooks | Hooks | Scenario failure screenshot hook implemented | Completed | Medium | Reporting
CCM-012 | Hooks | Hooks | Scenario-end logout and browser cleanup | In-Progress | High | Teardown
CCM-013 | Framework | CI/CD | Azure DevOps Maven pipeline | Pending | High | CI/CD
CCM-014 | Framework | CI/CD | Publish Allure results as pipeline artifact | Pending | Medium | CI/CD
CCM-015 | Login | Authentication | Valid user login | Completed | High | Smoke
CCM-016 | Login | Navigation | Navigate Commercial to Commodity Contract Management | Completed | High | Smoke
CCM-017 | Login | Navigation | Navigate to Create Contract screen | Completed | High | Smoke
CCM-018 | General | Mandatory Fields | Verify mandatory asterisk for multiple fields | In-Progress | High | Validation
CCM-019 | General | Mandatory Fields | Reusable validation accepting N field names as String | Completed | High | Validation
CCM-020 | General | Class | Select and verify Class | Completed | High | Functional
CCM-021 | General | Pricing | Select and verify Pricing | Completed | High | Functional
CCM-022 | General | Billing Location | Select and verify Billing Location | Completed | High | Functional
CCM-023 | General | Shipping Location | Select and verify Shipping Location | Completed | High | Functional
CCM-024 | General | Trader | Verify Trader auto-populates based on logged-in user | Completed | Medium | Functional
CCM-025 | General | Season | Select and verify Season | Completed | High | Functional
CCM-026 | General | Contract Number | Generate/capture Contract Number | Completed | High | Functional
CCM-027 | General | Contract Date | Enter and verify Contract Date | In-Progress | High | Defect/Validation |  | Date format issue observed
CCM-028 | General | Counterparty | Select and verify Counterparty | Completed | High | Functional
CCM-029 | General | Shipper | Select and verify Shipper | Completed | High | Functional
CCM-030 | General | References | Enter and verify CP Reference 1 and CP Reference 2 | Completed | Medium | Functional
CCM-031 | General | Exchange | Select and verify Exchange | Completed | Medium | Functional
CCM-032 | General | Fixation | Verify Fixation By and Fixation Terms | Completed | Medium | Functional
CCM-033 | General | Currency | Verify Invoice Currency and Price Currency/UOM | Completed | High | Functional
CCM-034 | General | Payment | Verify Payment Terms and Payment Terms Description | Completed | High | Functional
CCM-035 | General | Tax | Select and verify Tax Structure | Completed | High | Functional
CCM-036 | General | Withholding Tax | Select and verify With Holding Tax Structure | Completed | Medium | Functional
CCM-037 | Product Details | Single Product | Create one product row using JSON data | Completed | High | Data Driven
CCM-038 | Product Details | Multiple Products | Create multiple product rows using JSON arrays | Completed | High | Data Driven
CCM-039 | Product Details | Product | Select Product for dynamic row | Completed | High | Functional
CCM-040 | Product Details | Units | Enter Units value | Completed | High | Functional
CCM-041 | Product Details | Packing | Select Packing value | Completed | High | Functional
CCM-042 | Product Details | Quantity | Enter Quantity value | Completed | High | Functional
CCM-043 | Product Details | UOM | Select UOM value | Completed | High | Functional
CCM-044 | Product Details | Lots | Enter No Of Lots | Completed | Medium | Functional
CCM-045 | Product Details | Price | Enter Product Price | Completed | High | Functional
CCM-046 | Product Details | Target Type | Select Target Type | Completed | Medium | Functional
CCM-047 | Product Details | Target Date | Enter Target Date Range | Completed | High | Functional
CCM-048 | Product Details | Trade Month | Select Trade Month | Completed | Medium | Functional
CCM-049 | Product Details | Position Month | Select Position Month | Completed | Medium | Functional
CCM-050 | Product Details | Quality | Select Quality | Completed | High | Functional
CCM-051 | Product Details | Certification Premium | Enter Certification and Premium details | Completed | High | Functional
CCM-052 | Product Details | Dynamic Row | Add product row dynamically using Add Row control | Completed | High | Dynamic UI
CCM-053 | Product Details | Row Validation | Verify every product row against JSON test data | Pending | High | Validation
CCM-054 | Product Details | Negative Quantity | Verify invalid or empty Quantity validation | Pending | Medium | Negative
CCM-055 | Product Details | Negative Price | Verify invalid or empty Price validation | Pending | Medium | Negative
CCM-056 | Product Details | Date Validation | Verify invalid Target Date Range validation | Pending | Medium | Negative
CCM-057 | Commission | Single Commission | Create one commission row using JSON | Completed | High | Data Driven
CCM-058 | Commission | Multiple Commission | Create N commission rows using JSON array | Completed | High | Data Driven
CCM-059 | Commission | Agent Broker | Select Agent/Broker | Completed | High | Functional
CCM-060 | Commission | Reference Number | Enter Commission Reference Number | Completed | Medium | Functional
CCM-061 | Commission | Commission Type | Verify Percentage Flat and Value types | Completed | High | Functional
CCM-062 | Commission | Value | Enter Commission Value | Completed | High | Functional
CCM-063 | Commission | Value Unit | Select Commission Value Unit | Completed | High | Functional
CCM-064 | Commission | Data Matrix | Execute multiple commission value and unit combinations | Completed | High | Data Driven
CCM-065 | Commission | Row Validation | Verify every commission row against JSON | Pending | High | Validation
CCM-066 | Commission | Negative Value | Verify missing or invalid Commission Value | Pending | Medium | Negative
CCM-067 | Commission | Negative Unit | Verify missing Value Unit validation | Pending | Medium | Negative
CCM-068 | Other Sections | Delivery Terms | Enter and verify Delivery Terms/T&C | Completed | Medium | Functional
CCM-069 | Other Sections | Port Of Loading | Select and verify Port Of Loading | Completed | High | Functional
CCM-070 | Other Sections | Port Of Discharge | Select and verify Port Of Discharge | Completed | High | Functional
CCM-071 | Other Sections | Port Validation | Verify Port Of Loading and Port Of Discharge cannot be same | Completed | High | Negative
CCM-072 | Other Sections | Documents | Select required documents and checkboxes | Completed | Medium | Functional
CCM-073 | Other Sections | Remarks | Enter and verify Remarks | Completed | Low | Functional
CCM-074 | Workflow | Save | Save valid Commodity Contract | Completed | High | E2E
CCM-075 | Workflow | Create Success | Verify CONTRACT CREATED SUCCESSFULLY message | Completed | High | E2E
CCM-076 | Workflow | Pending Status | Verify newly created contract status is Pending | Completed | High | E2E
CCM-077 | Workflow | Approver | Execute Approver workflow | Completed | High | E2E
CCM-078 | Workflow | Approval Success | Verify CONTRACT APPROVED SUCCESSFULLY message | Completed | High | E2E
CCM-079 | Workflow | Approved Status | Verify contract status is Approved | Completed | High | E2E
CCM-080 | Workflow | Amendment | Open Copy By Contract and select Amendment | Completed | High | E2E
CCM-081 | Workflow | Amendment Data | Verify copied contract data in Amendment flow | Pending | High | Workflow
CCM-082 | Workflow | Amendment Fields | Verify fields that should be disabled after Amendment | Pending | High | Validation
CCM-083 | Workflow | Amendment Number | Verify Amendment Number and Amendment Date | Pending | High | Workflow
CCM-084 | Workflow | Amendment Save | Save amended contract and verify success | Pending | High | E2E
CCM-085 | Test Data | JSON Structure | Store contract test data in JSON | Completed | High | Maintainability
CCM-086 | Test Data | TestCaseId | Load test data using TestCaseId | Completed | High | Maintainability
CCM-087 | Test Data | Product Array | Support multiple product objects in JSON | Completed | High | Maintainability
CCM-088 | Test Data | Commission Array | Support multiple commission objects in JSON | Completed | High | Maintainability
CCM-089 | Test Data | Fail Fast | Fail before browser execution when TestCaseId is missing | Completed | Medium | Maintainability
CCM-090 | Gherkin | Reusable Steps | Use reusable generic step for multiple validation fields | Completed | High | Maintainability
CCM-091 | Locators | PrimeNG Table | Identify visible headers and map them to body columns | Completed | High | Locator
CCM-092 | Locators | Hidden Columns | Handle hidden Lot No/dynamic table columns | Completed | High | Locator
CCM-093 | Locators | Dynamic Rows | Use row-relative locators for dynamic product rows | Completed | High | Locator
CCM-094 | Locators | Mandatory Asterisk | Use robust XPath for field label and mandatory marker | Completed | High | Locator
CCM-095 | Locators | Locator Refactoring | Replace brittle index-based locators with stable attributes/relationships | Pending | High | Refactoring
CCM-096 | Validation | Field Retention | Verify entered values remain after moving between fields | Pending | High | Validation
CCM-097 | Validation | Required Fields | Submit blank form and verify required-field messages | Pending | High | Negative
CCM-098 | Validation | Save Error | Verify page/API save failure message | Pending | High | Negative
CCM-099 | Validation | Toast | Create reusable reliable validation for short-lived toast messages | Pending | Medium | Validation
CCM-100 | Validation | Dropdown Negative | Verify mandatory dropdown validation when no value is selected | Pending | Medium | Negative
CCM-101 | Validation | Duplicate Data | Validate duplicate/invalid business data scenarios | Pending | Medium | Negative
CCM-102 | Validation | Boundary Data | Verify zero decimal minimum and maximum numeric values | Pending | Medium | Boundary
CCM-103 | Execution | Smoke Suite | Create stable CCM Smoke test tag/suite | Pending | High | Execution
CCM-104 | Execution | Regression Suite | Create complete CCM Regression suite | Pending | High | Execution
CCM-105 | Execution | Failure Recovery | Verify browser cleanup after failed scenarios | Pending | Medium | Execution
CCM-106 | Execution | Parallel Execution | Evaluate driver isolation and parallel execution | Pending | Medium | Performance
CCM-107 | Reporting | Allure Metadata | Add environment/test metadata to Allure report | Pending | Low | Reporting
CCM-108 | Reporting | Allure Artifacts | Attach screenshots and useful evidence for failed scenarios | In Progress | Medium | Reporting
CCM-109 | CI/CD | Pipeline Execution | Execute CCM Maven tests through Azure DevOps | Pending | High | CI/CD
CCM-110 | CI/CD | Pipeline Reporting | Publish test results and Allure artifacts from pipeline | Pending | Medium | CI/CD

## To Add
ID | Area | Module | Scenario / Checklist Item | Status | Priority | Category | Execution Result | Defect / Reference | Notes
CCM-111 | Test Data | Captured Values | Save captured runtime values (e.g. Contract No.) to values.properties and capturedValues.json per TestCaseId | In Progress | High | Data Driven |  |  | In progress now: TestContext + updateTheValueInJsonFile
CCM-112 | Test Data | Captured Values Read | Read the captured Contract No. back by TestCaseId in Approver and Amendment steps | In Progress | High | Data Driven |  |  | Removes hard dependency on values.properties
CCM-113 | Validations | CCM Create | Verify Price Currency/UOM is reflected in Commission Details → Value Unit when Flat Amount is selected.
CCM-114 | Validations | CCM Create | Verify all mandatory field validations are displayed when Save is clicked without entering required details.
CCM-115 | Test Data | Schema Validation | Validate JSON test data (required keys, product and commission arrays) before the browser starts | Completed | Medium | Maintainability |  |  | Extends CCM-089 from missing TestCaseId to missing fields
CCM-116 | Execution | Retry | Retry analyzer for flaky failures (max 1 retry) with retry count visible in Allure | Pending | Medium | Execution |  |  | Keep off for defect scenarios
CCM-117 | Execution | Environment | Switch URL and credentials per environment (QA/UAT) through a Maven -D property | Pending | High | Execution |  |  | Needed before the Azure DevOps pipeline (CCM-109)
CCM-118 | Execution | Traceability | Tag every Cucumber scenario with its CCM ID so results map back to this sheet | Pending | Medium | Reporting |  |  | e.g. @CCM-077
CCM-119 | Execution | A | Run Smoke suite on Chrome and Edge | Completed | Low | Execution
CCM-120 | Reporting | Allure History | Keep Allure history and trends between pipeline runs | Pending | Low | Reporting |  |  | Link to CCM-110
CCM-121 | Workflow | Reject | Approver rejects a contract; verify rejection message and Rejected status | Pending | High | E2E |  |  | Confirm with app: reject flow exists
CCM-122 | Workflow | Modify/Edit Pending | Edit a Pending contract before approval and verify changes are saved | Pending | Medium | Workflow |  |  | Confirm with app
CCM-123 | Workflow | Cancel Create | Cancel the Create Contract screen and verify nothing is saved | Pending | Medium | Negative
CCM-124 | Workflow | View Approved | Verify an Approved contract opens read-only (fields disabled) | Pending | Medium | Validation
CCM-125 | Workflow | Amendment History | Verify status and history of original vs amended contract after Amendment approval | Pending | Medium | Workflow |  |  | Extends CCM-084
CCM-126 | Contract List | Search By Contract No | Search the list by captured Contract No. and verify the correct row is returned | Completed | High | Functional |  |  | Your capture step already reads the list column
CCM-127 | Contract List | Filters | Filter list by Status, Counterparty and Date range | Pending | Medium | Functional
CCM-128 | Contract List | Grid Behaviour | Verify pagination, sorting and column visibility on the list | Pending | Low | Functional
CCM-129 | Calculations | Product Totals | Verify product row total and contract total (Quantity x Price) | Pending | High | Validation |  |  | Confirm formula with BA
CCM-130 | Calculations | Commission Amount | Verify commission amount for Percentage, Flat and Value types | Pending | High | Validation |  |  | CCM-064 covers input combinations, not the calculated result
CCM-131 | Calculations | Tax Amounts | Verify Tax and Withholding Tax amounts for the selected structures | Pending | Medium | Validation |  |  | Confirm formula with BA
CCM-132 | Product Details | Delete Row | Delete a product row and verify remaining rows and totals | Pending | Medium | Dynamic UI
CCM-133 | Product Details | Many Rows | Add 10+ product rows and verify row-relative locators still hold | Pending | Low | Dynamic UI |  |  | Link to CCM-093
CCM-134 | Product Details | Date Rules | Target Date From not after To; Trade Month / Position Month consistency | Pending | Medium | Negative |  |  | Confirm rules with BA
CCM-135 | Commission | Delete Row | Delete a commission row and verify remaining rows | Pending | Medium | Dynamic UI
CCM-136 | General | Dependent Dropdowns | Verify Billing, Shipping and Shipper options depend on the selected Counterparty | Pending | Medium | Functional |  |  | Confirm with app
CCM-137 | General | Contract Date Retest | Retest Contract Date after the date-format defect is fixed | Pending | High | Defect/Validation |  |  | Link to CCM-027
CCM-138 | Login | Session | Verify logout and session-timeout behaviour | Pending | Low | Security